## Dashboard Summary
I. Requirements and Test Cases Coverage
Release Scope |  |  | Requirements | Test Cases | Unmapped Requirements | Unmapped Test Cases | Requirements Coverage | Test Cases Coverage
Total |  |  | 66 | 66 | 0 | 0 | 100% | 100%
| Within Scope of New Release |  | 3 | 3 | 0 | 0 | 100% | 100%
| Existed in Previous Release |  | 63 | 63 | 0 | 0 | 100% | 100%
Total (unique) |  |  | 97 | 98
| Requirements | Test Cases |  | Requirements | Test Cases
Old | 63 | 63 | Mapped | 66 | 66
New | 3 | 3 | Unmapped | 0 | 0
II. Test Cases Executed (by Test Priority)
Platform
Test Priority |  | Test Cases | QA Server | Staging Server | Production Server
Total |  | 66 | 66 | 0 | 0
5
4
| 3 | 66 | 66
2
1
NA
in Primary Platform
Executed | 66 |  | Executed | Not Executed
Not Executed | 0 | 5 | 0 | 0
|  | 4 | 0 | 0
|  | 3 | 66 | 0
|  | 2 | 0 | 0
|  | 1 | 0 | 0
|  | NA | 0 | 0
III. Summary of Current Test Results
Platform
Test Cases and Results |  |  |  | QA Server | Staging Server | Production Server
Total Number of Test Cases |  |  |  | 98 | 98 | 98
| Test Cases Executed or To Be Performed |  |  | 98 | 7 | 0
|  | Test Cases Executed |  | 98 | 7 | 0
|  |  | Passed | 89 | 6 | 0
|  |  | Failed | 9 | 1 | 0
|  | Test Cases Not Executed |  | 0 | 0 | 0
|  |  | Blocked | 0 | 0 | 0
| Test Cases Not To Be Performed |  |  | 0 | 91 | 98
|  |  | Deferred | 0 | 0 | 0
| % Test Cases Executed or To Be Performed (of Total Number of Test Cases) |  |  | 100% | 7.143% | 0%
|  | % Test Cases Executed (of Test Cases To Be Performed) |  | 100% | 100% | 0%
|  |  | % Passed (of Executed) | 90.82% | 85.71% | 0%
| QA Server | Staging Server | Production Server
Total Number of Test Cases | 98 | 98 | 98
Test Cases Executed or To Be Performed | 98 | 7 | 0
Test Cases Executed | 98 | 7 | 0
Passed | 89 | 6 | 0
Failed | 9 | 1 | 0
Blocked | 0 | 0 | 0
Test Cases Not Executed | 0 | 0 | 0
Test Cases Not To Be Performed | 0 | 91 | 98
Deferred | 0 | 0 | 0
Copyrighted 2010
NCI CBIIT
All Rights Reserved
Note on A3: Release Scope of Requirement/Test Case
Note on D3: Number of Requirements
Note on E3: Number of Test Cases
Note on F3: # of Requirements not mapped to a Test Case
Note on G3: # of Test Cases not mapped to a Requirement
Note on H3: % Mapped Requirements
Note on I3: % Mapped Test Cases
Note on A27: Number of Test Cases based on Test Priority
Note on D28: Primary, Secondary and Tertiary Platforms as defined in Project Summary worksheet
Note on A29: Test Priority on a scale of 1 to 5
Note on C29: # of Test Cases with this Priority
Note on D29: # of Test Cases executed on this platform
Note on E29: # of Test Cases executed on this platform
Note on F29: # of Test Cases executed on this platform
Note on B36: Not Available
Note on E57: Primary, Secondary and Tertiary Platforms as defined in Project Summary worksheet
Note on A59: = Test Cases To Be Performed + Test Cases Not To Be Performed
Note on B60: = Test Case Executed + Test Cases Not Executed
Note on C61: = Passed + Failed

## Project Summary
Project Information
General Information
Product: | caMOD
Release: | 2.6.2
Test Area: | caMOD
Test Case Owner: | Jianguo Li, Madhavi Kambampati
Start Date: | 2010-06-29
Reference Documents: | caMOD_V2.6.2
System Test Platform Information
Primary Platform: | QA Server
Secondary Platform: | Staging Server
Tertiary Platform: | Production Server
Tier Dates
| Estimated | Actual
Enter QA Date:
Enter Stage Date:
Enter Prod Date:
Requirement Delivered Date
% Test Cases Developed
BDA Certified (Yes/No)
Tag Dates
Tag | Date Tag was Delivered | # Requirements Delivered
Test Plan
Small paragraph describing the plan to test this application. This may include what type(s) of testing will be used, the approach to testing, and other relevant details.
Project Summary Report
This paragraph should summarize the end result of testing. Fill out this paragraph when test execution is complete. Official approval is recorded in the Document History/Approval tab. Submit this same summary via email to PM, QA Manager, and other relevant team members.

## Test Cases
|  | Test Cases for: caMOD v2.6.2 | [9 empty] | QA Server | [8 empty] | Staging Server | [9 empty] | Production Server
Test Case ID | Test Description/Purpose | Test Priority | Procedure | Category/Module | PreRequisite | Expected Results | Requirement ID | Requirement Description | Requirement Reference | Release Scope | asdf | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | Prevent Release | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | Prevent Release | asdf | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | asdf
14379 | Make sorting meaningful for humans and not for computers | 4 | Most of the drop down lists on our pages are sorted the "Java way": first numbers, then upper case letters and then lower case letters. It would be nice to convert this to a sorting that lists numbers first and then letters without regard to upper and lower case. Other issues: Species drop down list is alphabetically by the Latin name of the species which is listed after the common name for each species. That is confusing. Either list the Latin name first or sort by common name. | Regression Test |  | Sorting is more meaningful | Req_14379 | New Requirement for this release | UC_3.4.1 | O |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
14560 | Separation between keyword search and simple/advanced search is not obvious to user | 4 | Step 1: Log in to caMOD application. Step 2: Click "search Models". Step 3: Click Simple search/Advance Search. Step 4: Verify that there is more space between keyword search and simple search. Step 5: Verify that there is one more search button in the top for advance search. Step 6 : Verify that key word search is renamed. | Regression Test |  |  | Req_14560 | New Requirement for this release | UC_3.5.1 | O |  | Y | F | Not enough space between Keyword Search and Simple Search. | 2010-09-07 | 2.6.2 | DL
18438 | Change label from MMHCC Repository to NCI Mouse Repository | 5 | Step 1 : Enter caMOD application. Step 2: Create a model by entering all required fields in Model characteristic pages. Step 3:Click Animal Availability link. Step 4: Verify that Avaiable from MMHCC Repository label is changed to NCI Mouse Repository | New Feature |  | Under Animal Availability link MMHCC repository label is changed to NCI Mouse Repository | Req_18438 | New Requirement for this release | UC_3.1.1 | O |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
19879 | Display PMID number on search results detail page | 4 | Step 1: Access caMOD application. Step 2: Click Search models and click Advance search. Step 3: Enter a valid pubmed ID, such as 11751630 and search for a model. Step 4: From the result page click the model and navigate to publication page of the model. Step 5: Verify that in publication page pubmed ID icon is replaced with PMID number. | New Feature |  | Pubemed ID icon is replaced with PMID number. | Req_19879 | New Requirement for this release | UC_3.6.1 | N |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
20593 | Entered date changes every single time the model characteristics page is changed | 5 | Step 1: Enter caMOD application. Step 2: Create a model by entering all required fields in Model Characteristic page. Step 3: Verify that the Date Entered is the date that you first enter the model Step 4: Modify the model characteristics page the next day and verify that the Date Entered on the submit models list page does not change. | New Feature |  | Date entered column in Submit page shows the date , that the user first enter the model and remains the same in future and is not changed when the user modifies any field on the model characteristics page. | Req_20593 | New Requirement for this release | UC_3.2.1 | N |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
23750 | Links to sid, gif, jpeg, jpg, tif images needs to be modified for caIMAGE upgrade | 4 | Step 1: Log in to caMOD application. Step 2 : Create a new model by entering all required fields in Model Characteristic pages. Step 3: Cick "Enter Image" under IMAGES and try to upload images of type .jpg, .jpeg, .png and .gif Step 4: Click "Enter Transgene" under "Genetic description" , try to upload image of type .jpg, .jpeg, .png and .gif Step 5: Click "Enter Targeted Modification" under "Genetic Description" , try to upload image of type .jpg, .jpeg, .png and .gif | New Feature |  | User is able to upload images of type .jpg, .jpeg, .gir, .png and the data is saved successfully. | Req_23750 | New Requirement for this release | UC_3.8.1 | N |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
27533 | Change zebrafish concept codes to accommodate new NCI Thesaurus release with improved zebrafish vocabularies | 4 | Step 1: Log in to caMOD application. Step 2 : Create a new model by entering all required fields in Model Characteristic pages, Select Zebrafish species. Step 3: Select organ for Zebrafish (find valid one from database). Step 4: Click "Submit models" and enter a Zebrafish model. Step 5: Click "Enter Histopathology" under Histopathology and click "Site of Lesion/tumor". Step 6: Click "Enter Transgene" under Genetic Description and select "origin of species" as Zebrafish. Step 7: Click "Enter Assoc Expression" under "Enter Transgene" and click "Organ" button for Zebrafish. Step 8: Click "Cell line" and "Enter Cell line" and click organ button for Zebrafish. Step 9: Click "Transplantation" , "Enter Transplantation" and select donor species as "Zebrafish" and click "Organ" button for Zebrafish. Step 10: Click "Therapeutic Approaches", "Enter Therapy" and then click "Developmental Stage" button for Zebrafish. | New Feature |  | Zebrafish organ is retrieved from EVS and displayed successfully. All the existing models with Zebrafish organ or developmental stage data and searches for each model to verify that the organ is retrieved from EVS using the new concept_code format (colon instead of underscore). | Req_27533 | New Requirement for this release | UC_3.10.1 | N |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
27700 | Can't enter "Other" for site of administration on Transplant page | 5 | Step 1: Enter caMOD application. Step 2: Create a model by entering all required fields in Model Characteristic page. Step 3: Click the link for "Transplantation". Select "Other" in Site Of Administration choice box. Step 4: Enter some values for "Other Sites of Administration" and save the data. Step 5 : Now move the model status to "Complete" Step 6 : Now search for the model that you enter. Verify that the value entered in "other sites of Admin" in Transplantation is the same data that you enter. Now edit the data and save. Step 7 : Again search for the same model and verify that the edited value matches the value that you enter. | New Feature |  | The entered/edited value is stored properly in the DB and reflected properly in the GUI | Req_27700 | New Requirement for this release | UC_3.3.1 | N |  | Y | P | Expected | 2010-09-07 | 2.6.2 | DL
690 | Validate user guide and help links works well through out the application. The list of screens attached to JIRA item # CAMOD-690. | 4 | Step1. Open caMOD application. Step2: Go through each screen for the attched spread sheet and click on the link as specified in column D. | Bug Fix |  | Help link should open from link from column D. | Req_690 | User Guide and Help links throw HTTP Status 404 error on all tiers | CAMOD-690 | N |  | Y | P | Pass | 2010-09-02 | Build 1 | Madhavi
690-comment | Verify the formatting is good for page title = Submit and Edit Models. | 4 | Log into the submit models page with the following credentials: camodcurator2 Pw: DataEntry2! curatorcamod PW: 14And14=28 camodcurator PW: DataEntry1! Check formatting of the Submit/Edit Page. | Bug Fix | Log into the submit models page with the following credentials: camodcurator2 Pw: DataEntry2! curatorcamod PW: 14And14=28 camodcurator PW: DataEntry1! |  | Req_690-comment |  |  | N |  | Y | P | Expected | 2010-09-23 | Build 2 | DL |  |  |  | Y | F | the formatting was OK for the first user (curatorcamod,14And14=28) but it was messed up for the other two users (shifted to the right). | 2010-09-23 | Build 2 | DL
916_1 | Verify integration of caMOD with LexEVS 5.x | 4 | 1. Search for a mouse model such as Wnt 1 transgenics x p53 +/+. Verify that they retrieve Organ/Tissue and disease information on the histopathology page. 2. Search for a rat model such as Albumin-SV40 Tag. Verify that they retrieve antomy and disease information on the histopathology page. 3. Search for a zebra fish model such as XEF1-TEL-AML1. Verify that they retrieve antomy information on the histopathology page. | New Feature |  |  | Req_916_1 | EVS API 4.2 is going to be retired in 2010. | CAMOD-916 | N |  | Y | P | Pass | 2010-09-23 | Build 1 | DL |  |  |  | Y | P | Expected | 2010-09-23 | Build 2 | DL
916_2 | Verify integration of caMOD with LexEVS 5.x | 4 | 1. Submit a test model for mouse which contains entries from all vocabularies including staining method on the image submission page and human anatomy on the transplantation submission page. On the Images page, click on the Select button under Staining Method: to bring up the list. To gain access to the human anatomy vocabulary on the transplantation submission page select HUMAN as DONOR SPECIES. 2. Repeat same procedure for a rat model. | New Feature |  |  | Req_916_2 | EVS API 4.2 is going to be retired in 2010. | CAMOD-916 | N |  | Y | P | Pass | 2010-09-23 | Build 1 | DL |  |  |  | Y | P | Expected | 2010-09-23 | Build 2 | DL
917_1 | Verify the integration of caMOD with caBIO 4.x | 4 | 1. Enter "Bcl" into the Model Name / Model Descriptor search field, submit search. 2. Match the model name to Bcl-x flneo/flneo and select the model. 3. Go to the Genetic Description page in the search section. 4. Find an Gene Identifier (Entrez number) on this page. Click it and find additional information provide by caBIO API. Repeat this procedure for Model Descriptor mdm2-/- p53-/-. | New Feature |  |  | Req_917_1 | Upgrade caMOD to use LexEVS 5.x to get data | CAMOD-917 | N |  | Y | P | Pass | 2010-09-23 | Build 1 | DL |  |  |  | Y | P | Expected | 2010-09-23 | Build 2 | DL
917_2 | Verify the integration of caMOD with caBIO 4.x | 4 | 1. Enter "Canine osteosarcoma treated with SPI-77 versus carboplatin" into the Model Name / Model Descriptor search field, submit. 2. Click on Therapeutic Approaches and go to the Therapeutic Approaches page. Check Current Clinical Trials on this page which is retrieved from caBIO. 3. Repeat the same procedure for Model Name / Model Descriptor = P190 BCR/ABL transgenic model for Ph-positive ALL. | New Feature |  |  | Req_917_2 | Upgrade caMOD to use LexEVS 5.x to get data | CAMOD-917 | N |  | Y | P | Pass | 2010-09-23 | Build 1 | DL |  |  |  | Y | P | Expected | 2010-09-23 | Build 2 | DL
952 | caMOD home page should open when the user attempts to open in second browser. | 4 | Step1: Open caMOD home page using URL: http://cancermodels-{tier}.nci.nih.gov/camod/ in first browser. Step2: Open another browser and navigate to caMOD home page using same URL. | Bug Fix |  | caMOD home page should open in second browser. | Req_952 | User gets a blank page when accessing the caMOD home page for the second time within one browser session. | CAMOD-952 | N |  | Y | P | Pass | 2010-09-23 | Build 2 | DL |  |  |  | Y | P | Pass | 2010-09-23 | Build 2 | DL
953 | Display of NSC number and CAS number on Carcinogenic Intervention page | 4 | 1. Go to Simple Search and enter model name, such as "hepatocellular carcinoma (HCC) induced chemically", "Pancreatic cancer in hamsters treated by COX inhibitor ibuprofen and FLAP inhibitor MK886" or "mouse hepatocarcinogenesis model", click Search. You can use advanced search/Carcinogenic Interventions - Chemical/Drug/ and search for models with Therapeutic Approaches data to find more models with NSC/CAS numbers. 2. Click on Carcinogenic Intervention link on the left. Chemical/Drug section displays the links for NSC number and CAS number. 3. Click on Therapeutic Approaches link on the left. Compound / Drug section displays the links for NSC number and CAS number. Actual Behavior: Some times only NSC Number and CAS Number labels are displaying, links disappeared. | Bug Fix |  | NCS and CAS number links should display all the time. | Req_953 | Display of NSC number and CAS number on Carcinogenic Intervention page | CAMOD-953 | N |  | Y | P | Pass | 2010-09-23 | Build 1 | Madhavi |  |  |  | Y | P | Pass | 2010-09-23 | Build 2 | DL
955 | Header display on Assigning Screener to Animal Model page does not look good | 3 | 2. Click on Carcinogenic Intervention and Therapeutic Approaches link on the left. Chemical/Drug section displays the links for NSC number and CAS number. | New Feature | Login to caMOD with Admin role. | Separator (Example ':') exists between "Assigning Screener to AnimalModel" and model name in the header. There is space between Animal and Model. | Req_953 | New Requirement for next release | CAMOD-955 | N |  | Y | F | Pass | 2010-09-15 | Build 1 | DL
T_0001 | To verify the login is working | 3 | Step 1:Access the camod application and login with your credentials | Regression Test | Test #2 | Successful login and the user is redirected to http://cancermodels-qa.nci.nih.gov/camod/ReturnUserModels.do?method=returnUserModels | Req_0001 | Old Requirement | GF # 17747 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0002 | To verify the quick links in the left menu are working | 3 | Step 1: Access camod application Step 2: verify that the menus under quick links are working (NCI HOME, NCICB HOME,EMICE WEBSITE,CANCER IMAGES DATABASE,NCICB SUPPORT,caMOD USER GUIDE, HELP) | Regression Test |  | All the quick links are working and not broken. | Req_0002 | Old Requirement | GF # 12308 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0003 | Verify release notes are working and updated | 3 | Step 1: Access caMOD applocation. Step 2: click on the release notes link. |  |  |  | Req_0003 | Old Requirement | UC_191 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0004 | Verify that the user guide is updated and accessible from the home page. | 3 | Step 1: Access caMOD application. Step 2: Verify that the user guide is updated and accessible. | Regression Test |  | User guide is updated and accessible. | Req_0004 | Old Requirement | UC_100 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0005 | Verify that Search models (keyword, simple and advance search) doesn't require user log in | 3 | Step 1: Access caMOD application. Step 2: From the home page click search models. | Regression Test |  | Search models doesn't require any user login. | Req_0005 | Old Requirement | UC_111 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0006 | Verify that Submit models require user login | 3 | Step 1: Access caMOD application. Step 2: Click submit models link from the home page. | Regression Test |  | Submit models require user login | Req_0006 | Old Requirement | UC_114 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0007 | Verify that "Register" link is working | 3 | Step 1: Access caMOD application. Step 2: click Register from the home page. | Regression Test |  | Register link is working and the user is directed to Register for an account interface. | Req_0007 | Old Requirement | UC_115 | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0008 | Verify that simple key word search is working | 3 | Step 1: Access caMOD application. Step2: click search models , input some model descriptor description in the key word search. | Regression Test |  | Search valid search results. | Req_0008 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi
T_0009 | Verify that simple search (model descriptor) is working | 3 | Step 1: Access caMOD application. Step 2: Click search for models - simple search. Step 3 : Enter a valid model descriptor/model name and search for the models | Regression Test |  | Search gives results. | Req_0009 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-06 | Build 1 | Madhavi | F
T_0010 | Verify that simple search (principal investigator) is woking | 3 | Step 1: Access caMOD application. Step 2: Click search for models - simple search. Step 3 : select a principal investigator name from the dropdown list. | Regression Test |  | Search gives valid results. | Req_0010 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0011 | Verify that Simple search (Species) | 3 | Step 1: Access caMOd application. Step 2 : Click search models. Step 3: Select a valid species from the drop down list. | Regression Test |  | Search gives valid results. | Req_0011 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0012 | Verify that Simple Search (Site of Lesion/Tumor) | 3 | Step 1: Access caMOD application. Step 2: Click Search models. Step 3: Enter valid Site of lesion/Tumor | Regression Test |  | Search gives valid results. | Req_0012 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0013 | Verify that Table of Contents link is working | 3 | Step 1: Access caMOD application. Step 2: Click "Search Models". Step 3: Click "TOC" | Regression Test |  | TOC is working | Req_0013 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0014 | Verify that (Phenotype) is working | 3 | Step 1: Access caMOD application. Step2: Click Advanced Search, type in "lung cancer" as the phenotype. | Regression Test |  | Advance search - phenotype search is working. | Req_0014 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0015 | Verify that (Genetic Description) is working. | 3 | Step 1: Access caMOD application. Step 2:Click "search Models" and then click "Advance search. Step 3 : Enter a valid genetic description search | Regression Test |  | Advance search - Genetic Description is working. | Req_0015 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0016 | Verify that Advanced Search (publication search) is working | 3 | Step 1: Access caMOD application. Step 2: click "search Models", advance search. Step 3: Enter a valid pubmed id for the model search. Such as: 10393862 | Regression Test |  | Advance search - Publication search is working. | Req_0016 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0017 | Verify that Advanced Search (Carcinogenic Intervention) is working | 3 | Step 1: Access caMOD application. Step 2: Click "search models" and advance search. Step 3: Enter a valid carcinogenic intervention search | Regression Test |  | Advance search - Carcinogenic Intervention is working. | Req_0017 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0018 | Verify that Advanced Search (Cell line) is working | 3 | Step 1: Access caMOD application. Step 2: Click search models, advance search. Step 3: Enter a valid Cell line search | Regression Test |  | Advance Search - Cell line is working | Req_0018 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0019 | Verify that Advanced Search (Therapeutic Approaches) is working | 3 | Step 1: Access caMOD application. Step 2: Click Search models, advance search. Step 3: Enter a valid Therapeutic search | Regressin Test |  | Advance Search - Therapeutic approach is working. | Req_0019 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0020 | Verify that Advanced Search (Histopathology) is working | 3 | Step 1: Access caMOD application. Step 2: Click Search models, advance search. Step 3: Check search for models with Metastasis under Histopathology. Step 4: Click Search. | Regression Test |  | Advance Search - Histopathology is working. | Req_0020 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0021A | Verify that Advanced Search (Transient Interference) is working | 3 | Step 1: Access caMOD application. Step 2: Click "Search models", "Advance Search" Step 3: Enter valid Transient Iterference search. | Regression Test |  | Advance Search - Transient Interference is working. | Req_0021A | Old Requirement |  | O |  | Y | F | No models exist for Transient Interference. Remove option? | 2010-09-15 | Build 1 | DL
T_0021B | Verify that Advanced Search (micoarray data) is working | 3 | Step 1: Access caMOD application. Step 2: Click Search models, advance search. Step 3: Enter a valid micoarray data search | Regression Test |  | Advance search - microarray data is working. | Req_0021B | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0022 | Verify that Advanced Search (Image data) is working | 3 | Step 1: Access caMOD application. Step 2: click search models, advance search. Step 3: Enter valid image data | Regression Test |  | Advance search - image is working. | Req_0022 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0023 | Verify that Advanced Search (Tool strain) is working | 3 | Step 1 : Access caMOD application. Step 2 : Click "Search models", advance search. Step 3: Enter valid tool strain | Regression Test |  | Advance search - tool strain is working | Req_0023 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0024 | Verify that Advanced Search (External data source) is working | 3 | Step 1: Access caMOD application. Step 2: click search models, Advance search. Step 3 : Select a value for "External data" from the dropdown | Regression Test |  | Advance search - external data source is working. | Req_0024 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0025 | Verify that Drug Screening search is working. | 3 | Step 1: Access caMOD application. Step 2: Enter a valid NSC number such as 605852 and select any of the check box and hit submit. | Regression Test |  | Drug Screen search is working | Req_0025 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0026 | Verify that "Add Model" is working. | 3 | Step 1: Access caMOD application. Step 2 : login with user credentials. Step 3 : Click submit models and then add model | Regression Test |  | User is directed to Model characteristic page. | Req_0026 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0027 | Verify that user can add to model characteristic page for a model | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and hit submit. | Regression Test |  | User gets a message saying that model is successfully added | Req_0027 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0028 | Verify that Genetic Description - Transgene can be added to model. | 3 | Step 1: Access caMOD application. Step 2: Login with user credentials. Step 3: Add model characteristic page, and then add genetic description - enter transgene page. | Regression Test |  | Transgene page gets added and the user gets a message. | Req_0028 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0029 | Verify that Genetic Description - Genomic segment can be added to model | 3 | Step 1: Access caMOD application. Step 2: Login with user credentials. Step 3: Add model characteristic page, and then add genetic description - Enter Genomic segment page and submit all pages | Regression Test |  | Genomic segment gets added and the user gets a message. | Req_0029 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0030 | Verify that Genetic Description - Targeted modification can be added | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Genetic description - Targeted modification and enter all required fields and hit submit. | Regression Test |  | Targeted moification gets added and a message confirming this. | Req_0030 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0031 | Verify that Genetic Desciption - Induced mutation page can be added to the model. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Genetic description - Induced mutation and enter all the required fields and and hit submit | Regression Test |  | Induced mutation is added and the user gets a message confirming this. | Req_0031 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0033 | Verify that Genetic Description - Spontaneous mutation can be added to model. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Genetic description - Spontaneous mutation and enter all required fields and hit submit | Regression Test |  | Spontaneous mutation is added and the user gets message confirming this. | Req_0033 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0034 | Verify that carcinogenic intervention - enter antibody page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter antibody and enter all required fields and hit submit | Regression Test |  | Enter antibody is added to model and user gets message confirming this. | Req_0034 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0035 | Verify that Carcinogenic intervention - Enter bacteria is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter bacteria and enter all required fields and hit submit. | Regression Test |  | Bacteria page details are added to model and the user gets a message to confirm this. | Req_0035 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0036 | Verify that Carcinogenic intervention - Enter Chemical/drug page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter chemical/drug and enter alll required fields and hit submit | Regression Test |  | Chemical/Durg page details are added | Req_0036 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0037 | Verify that Carcinogenic intervention - Enter Environmental factor page is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter environmental factor page, submit all required fields, and hit submit | Regression Test |  | Environmental factor page is added . | Req_0037 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0038 | Verify that Carcinogenic intervention - Enter Gene delivery page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - enter gene delivery and enter alll required fields and hit submit | Regression Test |  | Gene delivery page details are added. | Req_0038 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0039 | Verify that Carcinogenic intervention - Enter growth factor page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Growth factor and enter all required fields and hit submit | Regression Test |  | Growth factor page deails are added/updated. | Req_0039 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0040 | Verify that Carcinogenic Intervention - Enter Hormone page is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter hormone and enter all required fields and hit submit | Regression Test |  | Hormone page details are aded/updated. | Req_0040 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0041 | Verify that Carcinogenic Intervention - Nutritional Factor is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Nutritional page and enter all required fields and hit submit | Regression Test |  | Nutritional factor details are added/updated. | Req_0041 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0042 | Verify that Carcinogenic intervention - Enter Plasmid page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Plasmid and enter all required fields and hit submit | Regression Test |  | Plasmid page details are added. | Req_0042 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0043 | Verify that Carcinogenic Intervention - Enter Radiation page is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Radiation and enter all required fields and hit submit | Regression Test |  | Radiation page details are added. | Req_0043 | Old Requirement |  | O |  | Y | P | Drop down list has redundant entries | 2010-09-15 | Build 1 | DL
T_0044 | Verify that Carcinogenic Intervention - Enter Surgery/other is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter Surgery/other. Add all required fields and hit submit | Regression Test |  | Sugery page details are added | Req_0044 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0045 | Verify that Carcinogenic Intervention - Enter Viral treatmentis working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Carcinogenic intervention - Enter Viral Treatment, enter all required fields and hit submit | Regression Test |  | Enter viral treatment details are added. | Req_0045 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0046 | Verify that Transient Interference - Enter Morpholino is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Transient Interference - Enter morpholino and hit submit | Regression Test |  | Morpholino deatails are added. | Req_0046 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0047 | Verify that Transient Interference - Enter siRNA are working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Transient Interference - Enter siRNA and hit submit | Regression Test |  | siRNA details are added. | Req_0047 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0048 | Verify that Publications -enter publications are working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Publications - Enter publication enter data and hit submit. | Regression Test |  | publication details are added | Req_0048 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0049 | Verify that Histopathology - Enter histopatholigy is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Histopathology - Enter histopatholgoy and enter all required fields and hit submit | Regression Test |  | Histopathology details are added. | Req_0049 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0050 | Verify that Therapeutic approaches - Enter Therapy pages are working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Therapeutic approaches - Enter therapy and enter all required fields and hit submit | Regression Test |  | Theapy page details are added. | Req_0050 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0051 | Verify that Cell line - Enter cell line is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Cell line - Enter cell line and enter all required fields and hit submit. | Regression Test |  | Cell line details are added. | Req_0051 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0052 | Verify that Images - Enter images is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Images - Enter image and enter all required fields and hit submit. | Regression Test |  | Image details are added. | Req_0052 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0053 | Verify that Microarray data - Enter microarray is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click microarray - Enter microarray and enter all required fields and hit submit. | Regression Test |  | Microarray details are added. | Req_0053 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0054 | Verify that model availability - Available from jackson lab is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click model availability - Verify Available from Jackson Lab is working. | Regression Test |  | Model availability - Available from Jackson lab details are added. | Req_0054 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0055 | Verify that Model Availability - Available from NCI Mouse Repo is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click model availability - Verify Available from MMHCC Repo is working. | Regression Test |  | Model availability - Available from MMHCC repo details are added. | Req_0055 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0056 | Verify that Model Availability - Available from investigator is working | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click model availability - Available from investigator and enter all required fields. | Regression Test |  | Model availability - Available from investigator details are added. | Req_0056 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0057 | Verify that Model Availability - Available from zfin is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click model availability - Available from zfin and enter all required fields. | Regression Test |  | Model availability - Available from zfin details are added. | Req_0057 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0058 | Verify that Transplantation - Enter transplant is working. | 3 | Step 1: Access caMOD application. Step 2: Log in with user credentials. Step 3: click submit models and then add model. Step 4 : Enter data in model characteristic page and submit. Step 5: click Transplantation - Enter transplant and enter all required fields and hit submit | Regression Test |  | Transplantation details are added/ | Req_0058 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0059 | Verify that all required fields in Submission pages are required for submission. | 3 | Step 1: Access camod application. Step 2 : verify that all required fields are required before saving the record | Regression Test |  | All required fields are mandatory before saving the record. | Req_0059 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0060 | Verify that user can customize result page. | 3 | Step 1: Access caMOD. Step 2: Log in to the application with user credentials. Step 3: Click Customize Results from the left navigation and select the columns to customize. | Regression Test |  | User can able to customize search results. | Req_0060 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0061 | Verify that user can view saved query. | 3 | Step 1:Access caMOD. Step 2:log in with user credentials. Step 3: click view saved queries. | Regression Test |  | User can able to see the results which he is saved. | Req_0061 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0062 | Verify that user can view query history. | 3 | Step 1: Access caMOD applocation. Step 2:Log in to the application with user credentials. Step 3:Click view query history | Regression Test |  | User should able to see the history of the query that he searched. | Req_0062 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0063 | Verify that Admin - Administraion roles are working properly. | 3 | Verify that all Admin section is working as expected | Regression Test |  | As expected. | Req_0063 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0064 | Verify that user is able to logout from the application. | 3 | Step 1: Log in to caMOD application. Step 2: Log out of the application | Regreesion Test |  | User able to log out successfully | Req_0064 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0065 | Verify server.log after 3 bad logins | 3 | Step 1: Try to login caMOD badly for 3 times |  |  | Server.log should have some error messages. | Req_0065 | New Requirement | GF # 12236 | N |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0066 | Register user with funky characters. | 3 | Step 1: Resgister User - For first name and last name enter "&%$#$", |  | Application installed and Configured | The funny characters are trimmed and it is allowable. | Req_0066 | New Requirement | GF # 22345 | N |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0066A | Verify Mouse Anatomy Vocabularies for Simple Search pages. | 3 | Step 1: Click "Search Models". Step 2: Select Species: Mouse. Step 3: Click on Select under Site of Lesion/Tumor: | Regression Test |  | EVS tree is displayed and search gives results. | Req_0066A | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0066B | Verify Mouse disease vocabularies in Advance Search pages. | 3 | Step 1: Click "Search Models". Step 2: Select Species: Mouse. Step 3: Click on Select under Diagnosis | Regression Test |  | EVS tree is displayed and the search gives results | Req_0066B | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0066C | Verify Mouse anatomy vocabulary in submission page is working | 3 | Step 1: Click "Submit Models". Step 2: Log into caMOD application. Step 3: On Model Characteristics Page, select species = mouse. Step 3: Click "Enter Histopathology" Step 4: Click on Select under Site of Lesion/Tumor: | Regression Test |  | Connection to EVS tree is successful and the record is saved. | Req_0066C | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0066D | Verify Mouse disease vocabulary for Submission pages. | 3 | Step 1: Click "Submit Models". Step 2: Log into caMOD application. Step 3: On Model Characteristics Page, select species = mouse. Step 3: Click "Enter Histopathology" Step 4: Click on Select under Diagnosis: | Regression Test |  | Connection to EVS tree is successful. | Req_0066D | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0068 | Verify that log in page is not displayed unless the user submit a model | 3 | Step 1: Login to caMOD. Step 2: In the home page the user is not forced to login until unless he submits a model. |  | Test #1 | No login page in home page. | Req_0068 | New Requirement | GF # 21852 | N |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0069 | Verify Rat Anatomy Vocabularies for Simple Search pages. | 3 | Step 1: Access caMOD application Step 2: Click "Search Models". Step 3: Click "Simple search" Step 4: Select "Rat" species. Step 5: Click "Site of Lesion/Tumor" | Regression Test |  | EVS tree is displayed and search gives results. | Req_0069 | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0070 | Verify Rat disease vocabularies in Advance Search pages. | 3 | Step 1: Access caMOD application. Step 2: click "search Models" and click "Advance search". Step 3: Select "Rat" species, Click "Diagnosis" | Regression Test |  | EVS tree is displayed and the search gives results | Req_0070 | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0071 | Verify Rat Anatomy Vocabularies for Submission pages. | 3 | Step 1: Access caMOD application. Step 2: Log in to application and click "Submit" models. Step 3: In model characteristic page Select species as "Rat" and fill all required fields and save. Step 4: Click "Histopathology" and click Select under "site of lesion/tumor" | Regression Test |  | Connection to EVS tree is successful and the record is added successfully. | Req_0071 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0072 | Verify Rat disease vocabulary in submission page is working. | 3 | Step 1: Access caMOD application Step 2: Click "Search Models". Step 3: Click "Simple search" Step 4: Select "Rat" species. Step 5: Click "Histopathology" and click Select under Diagnosis | Regression Test |  | Connection to EVS tree is successful and the record is saved. | Req_0072 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0073 | Verify Zebrafish Vocabularies for Simple Search pages. | 3 | Step 1: Access caMOD application Step 2: Click "Search Models". Step 3: Click "Simple search" Step 4: Select "zebrafish" species. Step 5: Click "Site of Lesion/Tumor" | Regression Test |  | EVS tree is displayed and search gives results. | Req_0073 | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0074 | Verify Zebrafish disease vocabularies in Advanced Search pages. | 3 | Step 1: Access caMOD application. Step 2: click "search Models" and click "Advance search". Step 3: Select "Zebrafish" species, Click "Diagnosis" | Regression Test |  | EVS tree is displayed and the search gives results | Req_0074 | Old Requirement |  | O |  | Y | F | EVS tree fails to expand | 2010-09-15 | Build 1 | DL
T_0075 | Verify Zebrafish Anatomy Vocabularies for Submission pages. | 3 | Step 1: Access caMOD application. Step 2: Log in to application and click "Submit" models. Step 3: In model characteristic page Select species as "Mouse" and fill all required fields and save. Step 4: Click "Histopathology" and verify that by clicking "site of lesion/tumor" | Regression Test |  | Connection to EVS tree is successful. | Req_0075 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0076 | Verify Zebrafish developmental stage vocabulary in submission page is working | 3 | Step 1: Access caMOD application. Step 2: Log in to application and click "Submit" models. Step 3: In model characteristic page Select species as "zebrafish" and fill all required fields and save. Step 4: Click "Therapeutic approaches" and verify by click developmental stages button | RegressionTest |  | Connection to EVS tree is successful and the vocabulary is displayed. | Req_0076 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0077 | Verify Human anatomy vocabulary in submission page is working. | 3 | Step 1: Access caMOD application. Step 2: Log in to the application. Step 3: Click "Submit model" and add a model. Step 4: Click "Transplantation" and "Enter Transplant" Step 5: Verify that orgran/tissue select is connected to EVS tree | Regression Test |  | Connection to EVS tree is successful and the vocabulary is displayed. | Req_0077 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
T_0078 | Verify Staining method vocabulary in submission page is working. | 3 | Step 1: Access caMOD application. Step 2: Log in to the application. Step 3: Click "Submit model" and add a model. Step 4: Click "Images" and "Enter Images". Step 5: Verify that staining method select is connected to EVS tree. | Regression Test |  | Connection to EVS tree is successful and the vocabulary is displayed. | Req_0078 | Old Requirement |  | O |  | Y | P | Pass | 2010-09-15 | Build 1 | DL
Note on A2: Unique ID for Test
Note on B2: Short description or purpose of Test Case
Note on C2: Priority on a scale of 1 to 5
Note on D2: Steps for performing the Test Case
Note on E2: Category or Module of the Test Case
Note on F2: Pre-existing condition that must be met
Note on G2: Expected Result of steps performed in the Test
Note on H2: Unique ID for Requirement
Note on I2: Short description of Requirement
Note on J2: Reference to a source for the Requirement
Note on K2: Is the Requirement new in this Release?
Note on M2: Is this Test Case going to be performed?
Note on N2: Current test result for the latest build tested
Note on O2: Actual test result for each build tested
Note on P2: Date Test Case was executed
Note on Q2: Name of the Build tested on
Note on R2: Name of the person who performed the Test
Note on S2: Defect ID for Defect found during testing
Note on T2: Status on how the Defect is being resolved
Note on U2: Severity of the Defect on a scale of 1 to 5
Note on W2: Is this Test Case going to be performed?
Note on X2: Current test result for the latest build tested
Note on Y2: Actual test result for each build tested
Note on Z2: Date Test Case was executed
Note on AA2: Name of the Build tested on
Note on AB2: Name of the person who performed the Test
Note on AC2: Defect ID for Defect found during testing
Note on AD2: Status on how the Defect is being resolved
Note on AE2: Severity of the Defect on a scale of 1 to 5
Note on AG2: Is this Test Case going to be performed?
Note on AH2: Current test result for the latest build tested
Note on AI2: Actual test result for each build tested
Note on AJ2: Date Test Case was executed
Note on AK2: Name of the Build tested on
Note on AL2: Name of the person who performed the Test
Note on AM2: Defect ID for Defect found during testing
Note on AN2: Status on how the Defect is being resolved

## Document History and Approval
Document History and Approval
Record milestone changes and approval to this document including: * Submission to DEV * DEV Suggested Revisions * QA modification from DEV recommendations * DEV Approval * Submission to Project Manager * Project Manager Approval * Test Execution Complete - submitted to PM and QA Manager * Review of document * QA Manager Approval
Modified/Approved By | Date | Team/Role | Notes/Approval
Sima Pandja | 2010-09-07 | DEV | Completed Test Cases, submitted to DEV
qaProject Template
Version | 2.1.0
Last Updated | 2010-04-06
Changes from 2.0.3 | Rearranged columns in Test Cases worksheet; Moved Test Case columns to the left so that the User may freeze the first two columns (Test Case ID and Test Description/Purpose); Adjusted formulas in Dashboard Summary
Added light yellow background color to Test Priority column to indicate that it's a column that affects formulas in the Dashboard Summary
Changed background color of third testing platform (Production) so that it's not the same background color as the first set of columns

## Test Environment
Test Environment
QA Server
OS: | Development tier - Solaris (Unix)
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, Oracle
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other
Staging Server
OS: | Windows 2000
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, SQL Server 2000, Tomcat
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other
Production Server
OS: | Windows 2000
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, SQL Server 2000, Tomcat
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other